## Sheet1
Module | Task | SubTask | Owner | Start | End | Status | Comments
Inventory
| Superadmin admin Add inventory | Add/Edit/Delete |  |  |  | done
| Global Stock Split |  |  |  |  | done
| Superadmin admin DSC Stock Transaction | All transaction example add stock delete stock transfer to partner and dsc deduct by apply |  |  |  | done
| Superadmin admin Wallet Balance | Add/Edit/Delete |  |  |  | done
| Superadmin admin Wallet Balance Transaction | All transaction example add wallet money delete wallet money transfer to partner and dsc deduct by apply |  |  |  | not done
| Free Inventory(Show Free inventory in stock and commission report) | Add/Edit/Delete |  |  |  | done
|  | Display free inventory |  |  |  | done
|  | Commission invoice as per free inventory |  |  |  | done
| Wallet Balance (Shuffling) | Partner Request send to Admin superadmin on mail also |  |  |  | done
|  | Admin Superadmin Response |  |  |  | done
|  | Manage Transaction and filter |  |  |  | done
|  | Payment |  |  |  | done
|  | Create General invoice |  |  |  | done
| Inventory Shuffling | Partner Request send to Admin superadmin on mail also |  |  |  | done
|  | Admin Superadmin Response |  |  |  | done
|  | Manage Transaction and filter |  |  |  | done
|  | Payment |  |  |  | done
|  | Create GST invoice |  |  |  | done
| New Token Inventory | Add new Token with billing details to be filled |  |  |  | done | For billing details form Ref scan doc page 14
|  | Send admin request and accounts dept for billing |  |  |  | done
|  | Show Transaction |  |  |  | done
|  | Payment |  |  |  | done
|  | Create invoice |  |  |  | done
| Old Token Upgrade | Create invoice |  |  |  | done
|  | Show Transaction and filter |  |  |  | done
Apply DSC |  | Payment |  |  |  | done
| DSC type master addon |  |  |  |  | done
| Top of from(if data is pending ex mobile no photo doc etc then give remark box to enter remark and send to partner that remark on mail) |  |  |  |  | done
| Create Form To apply DSC | Add/Edit/Delete |  |  |  | done
|  | If select type like government,organization,foreign organization,document signer then show more fields during applying dsc |  |  |  | done | Ref Scan doc page 4
| Make Payment from Wallet |  |  |  |  | not done | One more option to add when apply DSC which will deduct money from wallet
| Billing Details form (Optional for Staff)(During Apply DSC Form) |  |  |  |  | done | Form ref scan doc page 3
After Apply DSC But Befor Verify
| Give Option to Enter Orderid of DSC |  |  |  |  | done
| Transfer DSC to Admin for Verification | Display List of Dsc to be verified |  |  |  | not done | semi done
|  | Show Details page to display data and approved |  |  |  | not done | semi done
|  | Give option to edit if something worng and approved |  |  |  | not done | semi done
After Apply DSC And After Verification from Admin | Transfer DSC to Staff and Accounts Dept |  |  |  |  | not done
| Create 2 Section in Account Login Only |  |  |  |  | not done
| 1) Pending Billing Details with filters | Show All Admin Approved DSC in 2 section 1)Done 2) Not Done by default all will be shown in not done |  |  |  | not done | 1) Done- All Billing Details Complete 2) Not Done - If Billing Details pending
|  | All Entry in Not Done list give option to fill billing Details of that DsC |  |  |  | not done
|  | After Filling Details give 2 option for that DSC 1) After approval 2) After Download |  |  |  | not done | This 2 option will be for NOT DONE List
| 2) Bill To be processed with filters | Display Data in 2 Section 1) After Approval 2) After Download |  |  |  | not done
|  | Give Option to Genterate Bill for DSC |  |  |  | not done | If a person DSC is completed Means if approved or downloaded then Bill Should be generated
|  | After Clicking on genterated bill Show all the details of Bill prefilled not editable Except by Super admin |  |  |  | in-progress | bill edit option given to remaining invoice
|  | Give Mail CheckBox to Send mail to partner/Appicant/Both |  |  |  | done | Means Give 3 option 1) Partner 2) Applicant 3) Both 4) None to send mail accordingly and there will be default checkbox to apply by default billing details for that partner for all the dsc
| Now In Staff Login Show List of Pending DSC | With Filter and Give Details button |  |  |  | done
| After Clicking on filter Button show details of DSC and give all the Stauts Options to update status | In Status List 7th point(Sent for approval) Give option to clear objection tab(IF DSC approved without any objection then hide objection tab) |  |  |  | not started | For Status Option Ref Scan Pdf Doc page 6
|  | After Entering Objection give 2 option 1) SMS 2) Email |  |  |  | not started
|  | In Status List 8th Point(Downloaded) Checkbox Should be disable until DSC is approved |  |  |  | not started
|  | In Status List 9th Point if DSC is rejected after approved then deduct it from inventory and if rejected before approved then return DSC inventory |  |  |  | not started
|  | After Clicking on Approved show more 2 option 1) New Token 2) Renewal |  |  |  | not started
|  | After Clicking on New Token Send request to admin and if admin approved send request to Account Dept to Generated Invoice for Token |  |  |  | not started
|  | If Renewal Selected show 2 option 1) Upgrade Token 2) Old Token |  |  |  | not started
|  | After Clicking on Old Token give 2 radio button 1) Download partner office(Any desk) 2) Download from Office and give 2 textbox to enter Mobile no and Name |  |  |  | not started
|  | After selecting status(Downloaded) give 2 optin 1) Online Mode 2) Offline Mode and give Datepicker to select download date by default todays date for renewal Management(Save automatically in renewal Management ) |  |  |  | not started
DSC Delivery
| Display all the offline Dsc download with filters |  |  |  |  | not started
| Give option to change the status of Delivery with 3 option 1) Send DSC thorugh courier 2) DSC Collected From Office 3) Delivered From our Office auto email for all 3 options | If select option 1(Send DSC through Courier) open form to fill details |  |  |  | not started | For Form Fields Ref Scan Pdf Doc page 8 only dsc part pending
|  | If select option 2(DSC Collected From office) open form to fill details |  |  |  | not started | For Form Fields Ref Scan Pdf Doc page 8
|  | If select option 3(Delivered From Our Office) open form to fill details |  |  |  | not started | For Form Fields Ref Scan Pdf Doc page 8
not started
| Multiple Order Id add or mark option required | if same partner Multiple dsc to deliver then select that dsc and fill same details for all example if 1 partner applied for 5 dsc he want 5 dsc send in courier then select 5 dsc and courier details will be same for all 5 |  |  |  | not started
Commission Report for both side Admin and partner login
| Admin | Give 2 option 1) Commission Generate 2) Commission Due |  |  |  | done
|  | Show list as per selected |  |  |  | in-progress
|  | Give add option to add/edit/delete |  |  |  |  | For Form Fields Ref Scan Pdf Doc page 9
|  | Show total Commission on top |  |  |  | in-progress
| Partner | Show transaction Listing |  |  |  | done
|  | Show total Commission on top |  |  |  | done
combine report screen
Renewal Management
| When Staff apply DSC that time search Existing Pan is there in DSC or not in renewal management | if found then give duplicate option if click then all the data will be autofilled including documents |  |  |  | not started
|  | after that give to 2 option 1) Mapped 2) Not Mapped |  |  |  | not started
|  | if clicked on mapped then replace existing entry to new one |  |  |  | not started
|  | if clicked on not mapped then new entry will be created |  |  |  | not started
| AMC Managemnt | partner change option required for DSC to direct |  |  |  | not started | if partner tells that he or she is not client of my so MDS can call directly to client and can change partner name to direct\
not started
| Renewal Remainder | Existing DSC Data import option |  |  |  | not started
|  | Partner can login and set renewal remainder of dsc ADD/Edit/Delete |  |  |  | not started | For Form Fields Ref Scan Pdf Doc Page 11
|  | Give both Option to partner for manually entry and bulk import also |  |  |  | not started
|  | if partner does not add any entry in renewal remainder from last 30 days then send remainder on mail 30 days/60days/90Days |  |  |  | not started
|  | Now send DSC renewal remainder to partner 1 day before expiry. Every 1st date of month and before expiry 30days/15days/7days/1day |  |  |  | not started | Means send all the DSC expired list of current month
|  | Send remainder after expiry of DSC also |  |  |  | not started | Every 30 days expired DSC
|  | And for Direct DSC send mail of DSC remainder to client and MDS also |  |  |  | not started
| Sublogin renewal remainder and entry module | Add DSC with Only OrderId when partner send to MDS Add/Edit/Delete |  |  |  | not started | For Form Fields Ref Scan Pdf Doc Page 12
|  | Show list of DSC with filter and give option to change the status of that DSC |  |  |  | not started | For Status list Ref Scan Pdf Doc page 12
|  | In status 3 (Objection) send auto email to partner with whatever objection is there to solve and after sending mail change the status of that DSC again to sent to capricon |  |  |  | not started
|  | In Status 5 (Reject DSC) Give undo option to Super admin and change DSC status again to send to capricon |  |  |  | not started
Reseller Sublogin | Give Option to add offers with date wise(start date end date) with defalut option |  |  |  |  | not started
| Client purchase recharge send request to admin and if admin approve than deduct balance from MDS wallet |  |  |  |  | not started
| if recharge with extra free money then don’t create general voucher show free money earn tab with total display and when clicking on tab that time display all the transaction |  |  |  |  | not started
| Give configration to super admin to configure minimum amount to request for recharge also give difference of amount he can request |  |  |  |  | not started | example if minimum balance is 1000 and difference is 500 then user can request 1000/1500/2000 etc
| when user is requesting money if he try to request which is in offer then show suggestion to request from offer |  |  |  |  | not started
Combo offer | make create offer page |  |  |  |  | not started
| request page from partner end with payment gateway |  |  |  |  | not started
| request page for partner from superamdmin login |  |  |  |  | not started
| report for combo offer |  |  |  |  | not started
| return process |  |  |  |  | not started

## Sheet2
DATE | PARTNER NAME | APPLICANT NAME | AMOUNT | ADD AMOUNT | TDS DEDUCTION | EMAIL
| MEHUL | V | 100 | 100
| VIRAJ | D | 200 | 200
| GAURAV | G | 140
| MEHUL | S | 450
| MEHUL | W | 100
| HARDIK | T | 1000